## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Collect and normalize network traffic data for ML model training. | MUST HAVE | Log Files/Threat Data | Deepak | 3- Completed
S1 | S1 | US-002 | Initial training and validation of the Random Forest Classifier model. | MUST HAVE | Scikit-learn, Data | Nageena | 3- Completed
S2 | S2 | US-003 | Set up the basic Cyber Threat Dashboard framework and deployment (Vercel). | MUST HAVE | Vercel/PostgreSQL | Jones | 3- Completed
S2 | S2 | US-004 | Develop live updating charts and metrics for the Dashboard. | MUST HAVE | Plotly, Live Event Feeds | Satwik | 3- Completed
S3 | S3 | US-005 | Implement the core logic for the Security Helper Chatbot (Rule-Based). | MUST HAVE | Rule-Based Chatbot | Teena | 3- Completed
S4 | S4 | US-006 | Build the Admin Panel feature for Offline Dataset Analysis upload. | MUST HAVE | Backend Optimization | ibrahim | 3- Completed
S5 | S5 | US-007 | Integrate ML model to classify real-time network traffic as Malicious/Benign. | MUST HAVE | Trained Random Forest Model | Purushotham | 3- Completed
S6 | S6 | US-008 | Develop logic for scanning IP/API endpoints and assessing risk (Moderate). | MUST HAVE | VirusTotal/AbuseIPDB | Nageena | 3- Completed
S7 | S7 | US-009 | Generate and display a Prioritized Action Plan based on threats. | MUST HAVE | Threat Classification | Jones | 3- Completed
S8 | S8 | US-010 | Final System Integration and bug fixing across all features. | MUST HAVE | All features complete | Deepak | 3- Completed
S8 | S8 | US-011 | Prepare documentation (Agile Log, Architecture) and final presentation (PPT). | MUST HAVE | Project Complete | Teena Shrivastava | 3- Completed
S8 | S8 | US-012 | Future planning: Define requirements for Gemini API Chatbot upgrade. | COULD HAVE | Gemini API | Purushotham | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Set up Vercel hosting, PostgreSQL, and basic dashboard framework. | 2025-10-06 | 2025-10-10 | purushotham &Teena | Setup/Deployment | 3- Completed
US-002 | 2 | Pre-process data (cleaning, null values) for initial Random Forest training. | 2025-10-11 | 2025-10-12 | ibrahim | Data Processing | 3- Completed
US-003 | 3 | Design and implement the basic layout and style of the dashboard UI. | 2025-10-13 | 2025-10-15 | jones | UI Development | 3- Completed
US-004 | 4 | Train and validate the initial Random Forest model (first iteration). | 2025-10-16 | 2025-10-19 | Teena | Model Training | 3- Completed
US-005 | 5 | Design System Architecture and create initial Agile documentation structure. | 2025-10-20 | 2025-10-23 | Nageena | Documentation | 3- Completed
US-006 | 6 | Research external APIs (VirusTotal) for IP/API scanner functionality. | 2025-10-24 | 2025-10-26 | Ibrahim | Research/Design | 3- Completed
US-007 | 7 | Implement Plotly for interactive data visualization (live charts). | 2025-10-27 | 2025-10-29 | Satwik | UI Integration | 3- Completed
US-008 | 8 | Develop the core rule-based logic for the Security Helper Chatbot. | 2025-10-30 | 2025-11-02 | purushotham | Logic Development | 3- Completed
US-009 | 9 | Develop Admin Panel UI for uploading offline .csv threat data. | 2025-11-03 | 2025-11-08 | jones | UI/Frontend | 3- Completed
US-010 | 10 | Implement data upload endpoint and backend optimization for large files. | 2025-11-09 | 2025-11-11 | Teena | Backend Optimization | 3- Completed
US-011 | 11 | Integrate ML model to classify real-time incoming network traffic. | 2025-11-12 | 2025-11-14 | nageena | ML Integration | 3- Completed
US-012 | 12 | Implement IP/API scanner functionality with external API calls. | 2025-11-15 | 2025-11-16 | deepak | API Integration | 3- Completed
US-013 | 13 | Research and initial design for the future Gemini API Chatbot integration. | 2025-11-17 | 2025-11-22 | deepak | Future Research | 3- Completed

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Lack of clarity on the required data format for the ML model's input. | Conducted a detailed discussion with Vishnu to define a standardized data schema.
Sprint 2 | Day 12 | Difficulty integrating the third-party API threat intelligence data due to inconsistent JSON structures. | A detailed explanation of data normalization techniques was given by Sanjay.
Sprint 3 | Day 20 | Unexpected server timeouts occurring when uploading large .csv files for model retraining in the Admin Panel. | Explained by the mentor by screen sharing on how to implement chunked data processing to prevent timeouts.
Sprint 3 | Day 25 | Difficulty in structuring and completing the initial project Agile documentation. | Dedicated internal team meeting for Agile Documentation review and delegation of sections.
Sprint 4 | Day 35 | Getting logical errors in the Security Helper Chatbot's response logic when handling complex threat queries. | Resolved via a meeting with Kanupriya and the team to refine the rule-based logic and error handling.
Sprint 4 | Day 40 | Final implementation challenges with Plotly to visualize real-time event feeds on the dashboard. | Resolved via a focused technical meeting with Shreya V and Priyanshi T to adjust visualization library settings.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-10-06 | 2025-10-17 | Purushotham | Implementing data chunking for large uploads. | Allowing backend timeouts with large log files. | Ensuring Vercel deployment stability for real-time analysis. | Backend optimization issue for file uploads solved.
2 | Sprint 3 | 2025-10-20 | 2025-10-31 | Teena | Proactive user testing on dashboard visuals. | Delayed debugging of minor UI/UX issues. | Delivering clear, interactive threat visualizations (Plotly). | Enhanced visual clarity and user experience.
3 | Sprint 4 | 2025-11-03 | 2025-11-10 | Nageena | Dedicated time for Agile documentation and Architecture. | Waiting for others to complete initial docs/diagrams. | Assisting with data consistency definitions. | Final documentation (Agile) and architectural clarity achieved.
4 | sprint 5 | 2025-11-11 | 2025-11-17 | Jones | Comprehensive end-to-end integration testing. | Focusing on minor aesthetic fixes in the final week. | Producing the final integrated platform. | Ensured all system features worked together seamlessly.